## Sheet1
QA DFESW2 Solo project Anthony Harrison
Impact
|  | Negligable | Minor | Moderate | Significant | Severe
| Very Likely | 5 | 10 | 15 | 20 | 25
| Likely | 4 | 9 | 14 | 19 | 24
Likelihood | Possible | 3 | 8 | 13 | 18 | 23
| Unlikely | 2 | 7 | 12 | 17 | 22
| Very Unlikely | 1 | 6 | 11 | 16 | 21
| Risk | Description | Response | Likelyhood | Impact | Score
| Computer breaks | My computer is quite old at this point. Although no issues have arose yet, it is always a possibility. | Have a laptop setup with the correct tools to continue the project with minimal downtime. | Possible | Significant | 18
| Internet outage | This is something that can just happen and could effect my ability to work with Jira and Github. | Have as much material as possible available if such a thing occurs. A mobile hotspot could also be used if deadlines are close. | Unlikely | Minor | 7
| Illness | The is currently a really bad cold/flu going around and it would be unfortunate to get it during this project. | Do what I can to meet the deadline but focust of health first. | Very unlikely | Severe | 21
| Childcare unavailable | If my childcare becomes unavailable I would be the next person to look after my child. | Work at a reduced capacity to the best of my ability while my child is here. | Possible | Moderate | 13
| Eye strain | With this being a solo project I may lose track of time and forget to take regular breaks. | Set alarms if headaches start and it becomes a recurring problem. | Unlikely | Negligable | 2
| Getting hung up on a problem | If I get stuck on a problem I may spend longer than nessasary on it rather than moving onto another task or taking a break. | Remember to step back from a problem and take time to breathe and think away from the computer. | Possible | Minor | 8
| Procrastination | I could begin procrastinating and wasting time for far longer than a normal break. | Remind myself of the deadline. | Very likely | Negligable | 5